## Sheet1
Tasks | Completion | Note
Extract prescription datasets and person-level covariates based on modified PrEP initiation definition and record exclusion criteria (n=17,054 persons) | Yes
Pre-process prescription data to binary PrEP sero-protection matrix | Yes
Obtain descriptive statistics and distribution plots for the source dataset (n=17,054) | Yes
Assess computational costs of GBTM model fitting under various optimization hyperparameter settings | Yes | The results shows that, on a local machine, the gold standard optimization of GBTM may be too costly on the source dataset. Consequently, we decided to lower the optimization hypermaters and limit the size of the input dataset for GBTM.
Implement iterative stratified sampling method to obtain the most representative sample dataset (n=4000 persons) according to the bivariate distributions among the person-level covariates (age, average copay, primary payer, duration of suboptimal PrEP protection). | Yes
Obtain descriptive statistics and distribution plots for the sample dataset (n=4,000) | In-progress
Fit GBTM on the sample dataset for k=2~6 and compute model fitness statistics. | Yes | Predicted PrEP sero-protection probabilities and observed PrEP sero-protection proportion trajectories by group membership are plotted for each k-group model
Assess model fitness and select two candidate k-group models for consensus clustering | In-progress
Assess computation costs of consensus GBTM and modify hyperparameters accordingly | In-progress | We may again modify the number of iterations run if the algorithm appears too computationally costly for Walgreens
Conduct consensus GBTM using the two selected k values, and assess consensus probability distributions | No | Assessment includes plotting histogram and CDF of the consensus probabilities, computing proportion of ambiguous clustering and average pairwise consensus probabilities per group
Conduct associational test between the baseline covariates and the identified group membership per the final k-group model | No | For the ZIP-3 level covariates, we will link the aggregated statistics informed by AIDS-view or Census to Walgreens' dataset based on the patients' ZIP-3 code
Sensitivity analysis | No | There are two potential sensitivity analyses we could do. We will decide which one to pursue after examine the base analysis results.
Number of PrEP users who have >=1 PrEP assessment intervals where interval lengths are > the adherent PrEP consumption period (days supply + 7 days) |  | of those, select 40
Number of non-daily PrEP users (10%) | 40
non-daily users (4 doses/week) | 20
non-daily user (5 doses/week) | 20